## Dashboard
AI-Powered Bug Tracker — Sprint Tracker
AIBT-2026 ¦ Project: Alok Ranjan ¦ April 2026 ¦ v1.0
Sprint Summary — live progress (auto-calculated from tracker sheets)
Sprint | Title | Phase | Tasks | Done | Progress
Sprint 1 | Foundation & Auth | Backend | 13
Sprint 2 | Bug CRUD APIs | Backend | 10
Sprint 3 | User Management APIs | Backend | 6
Sprint 4 | AI Integration | Backend | 8
Sprint 5 | Playwright Test Runner | Backend | 8
Sprint 6 | Email Notifications | Backend | 8
Sprint 7 | Testing & Hardening | Backend | 8
Sprint 8 | Setup & Auth UI | Frontend | 9
Sprint 9 | Admin Dashboard | Frontend | 10
Sprint 10 | Developer Dashboard | Frontend | 9
Sprint 11 | Tester Dashboard | Frontend | 9
Sprint 12 | Polish & QA | Frontend | 10
TOTAL PROJECT |  |  | 108
STATUS LEGEND
To Do | In Progress | Done | Blocked
HOW TO USE
1. Click any Sprint name above to jump directly to that sprint's task list.
2. On each sprint sheet, change the STATUS dropdown for each task (To Do / In Progress / Done / Blocked).
3. Dashboard progress % and Done counts update automatically via formulas — no manual entry needed.
4. Use the ASSIGNED TO column to note who owns each task.
5. Use the NOTES column for blockers, PR links, or completion notes.
6. PRIORITY is pre-filled (first 3 tasks = High, next 4 = Medium, rest = Low) — adjust as needed.

## S1-Auth
Sprint 1 — Foundation & Auth
Phase 1 — Backend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 13
# | Task Description | Status | Priority | Assigned To | Notes
1 | Create Spring Boot 3 project (Initializr: Web, JPA, Security, Validation, Lombok, PostgreSQL) | Done | High
2 | Configure application.properties — datasource, JPA DDL, server port | Done | High
3 | Design JPA entity: User (id UUID, name, email, password, role ENUM, phone, createdAt) | Done | High
4 | Design JPA entity: Bug (id UUID, title, description, severity, status, assignedTo FK, createdBy FK, timestamps) | Done | Medium
5 | Design JPA entity: TestScript (id UUID, bugId FK, code TEXT, status ENUM, logs TEXT, executedAt) | Done | Medium
6 | Implement Spring Security — SecurityFilterChain, JwtAuthFilter, JwtUtil | Done | Medium
7 | Token blacklist service for logout (in-memory Set or Redis) | Done | Medium
8 | Auth endpoint: POST /api/auth/signup (Tester only) | Done | Low
9 | Auth endpoint: POST /api/auth/login (all roles, returns JWT) | Done | Low
10 | Auth endpoint: POST /api/auth/logout (invalidate token) | Done | Low
11 | Role-based route protection: ADMIN, DEVELOPER, TESTER mapped to endpoint patterns | Done | Low
12 | Global exception handler (@RestControllerAdvice) — 401, 403, 404, 400 | Done | Low
13 | Unit tests for JwtUtil and AuthService | Done | Low

## S2-BugCRUD
Sprint 2 — Bug CRUD APIs
Phase 1 — Backend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 10
# | Task Description | Status | Priority | Assigned To | Notes
1 | POST /api/bugs — create bug (Admin or Tester) with field validation | Done | High
2 | GET /api/bugs — list all bugs (Admin); scoped list for Developer and Tester | Done | High
3 | GET /api/bugs/{id} — get single bug with associated TestScript | Done | High
4 | PUT /api/bugs/{id} — full update (Admin only): title, description, severity, assignee, status | Done | Medium
5 | DELETE /api/bugs/{id} — hard delete with cascade to TestScript (Admin only) | Done | Medium
6 | PATCH /api/bugs/{id}/status — Developer updates: Open / In Progress / Resolved / Closed | Done | Medium
7 | PATCH /api/bugs/{id}/cancel — Tester withdraws own bug (status = Withdrawn) | Done | Medium
8 | Request/response DTOs for all endpoints (manual mapping or MapStruct) | Done | Low
9 | @Valid + custom constraint validators: severity enum, status transition rules | Done | Low
10 | Integration tests for all Bug endpoints using MockMvc | Done | Low

## S3-UserMgmt
Sprint 3 — User Management APIs
Phase 1 — Backend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 6
# | Task Description | Status | Priority | Assigned To | Notes
1 | GET /api/users — list all users (Admin): id, name, email, role, phone, createdAt | Done | High
2 | PUT /api/users/{id} — Admin updates user: only email and phone editable | Done | High
3 | DELETE /api/users/{id} — Admin hard-deletes user; prevent self-deletion | Done | High
4 | PATCH /api/users/password — Tester changes own password with bcrypt verify | Done | Medium
5 | Password change validation: min-length, reject re-use of current password | Done | Medium
6 | Unit tests for UserService; integration tests for all User endpoints | Done | Medium

## S4-AI
Sprint 4 — AI Integration
Phase 1 — Backend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 8
# | Task Description | Status | Priority | Assigned To | Notes
1 | AiService: build prompt from bug title + description | Done | High
2 | Call Claude / Gemini / OpenAI API via RestTemplate or WebClient | Done | High
3 | Parse AI response: extract raw Playwright JS code block and sanitise | Done | High
4 | Save TestScript entity (code=AI output, status=PENDING) immediately after bug save | Done | Medium
5 | Make AI call asynchronous (@Async + ThreadPoolTaskExecutor) — bug returns 201 instantly | Done | Medium
6 | Handle AI API timeout (10s) and errors: mark status=AI_FAILED, do not block bug save | Done | Medium
7 | Config: AI provider URL, API key, model, temperature — all from application.properties / env | Done | Medium
8 | Unit tests for AiService with mocked HTTP client | Done | Low

## S5-Playwright
Sprint 5 — Playwright Test Runner
Phase 1 — Backend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 8
# | Task Description | Status | Priority | Assigned To | Notes
1 | PlaywrightRunnerService: write AI JS code to temp file /tmp/aibt/<bugId>.spec.js | Done | High
2 | Execute via ProcessBuilder: ['node', tempFilePath] with 30s timeout | Done | High
3 | Capture stdout + stderr; parse exit code: 0=PASS, non-zero=FAIL | Done | High
4 | Update TestScript: status=PASS/FAIL, logs=<output>, executedAt=now() | Done | Medium
5 | Chain execution immediately after AI generation (CompletableFuture chain) | Done | Medium
6 | GET /api/bugs/{id}/test-result — returns TestScript for frontend polling | Done | Medium
7 | Verify Node.js and Playwright installed in runtime; document setup steps in README | Done | Medium
8 | Integration test: submit dummy bug, verify TestScript status transitions | Done | Low

## S6-Email
Sprint 6 — Email Notifications
Phase 1 — Backend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 8
# | Task Description | Status | Priority | Assigned To | Notes
1 | EmailService: wrap Brevo SMTP or Brevo Transactional REST API; inject credentials from env | Done | High
2 | Email template 1 — Bug Created: to assigned Developer (title, severity, description, link) | Done | High
3 | Email template 2 — Bug Updated (Admin edit): to Developer + Tester (changed fields) | Done | High
4 | Email template 3 — Status Changed (Dev action): to Tester + Admin (new status highlighted) | Done | Medium
5 | Email template 4 — Bug Withdrawn (Tester cancel): to assigned Developer | Done | Medium
6 | Email template 5 — Test Result: to Tester (PASS/FAIL badge, truncated logs) | Done | Medium
7 | All emails sent asynchronously (@Async) — do not block API response | Done | Medium
8 | Integration test: mock Brevo API, verify correct recipients and subjects per event | Done | Low

## S7-Hardening
Sprint 7 — Testing & Hardening
Phase 1 — Backend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 8
# | Task Description | Status | Priority | Assigned To | Notes
1 | @PreAuthorize on every controller method verified against role matrix | To Do | High
2 | JWT expiry, signature validation, and blacklist tested under adversarial inputs | To Do | High
3 | Input sanitisation: reject script tags and SQL patterns in free-text fields | To Do | High
4 | Rate limiting on POST /api/auth/login (5 attempts/min via Bucket4j or custom filter) | To Do | Medium
5 | CORS configuration: whitelist React dev server and production domain only | To Do | Medium
6 | Full integration test suite: auth, bug CRUD, AI mock, email mock, test runner mock | To Do | Medium
7 | SpringDoc OpenAPI / Swagger UI at /swagger-ui.html — document all endpoints | To Do | Medium
8 | Code review, refactor, and performance baseline check (CRUD < 200ms) | To Do | Low

## S8-FE-Auth
Sprint 8 — Setup & Auth UI
Phase 2 — Frontend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 9
# | Task Description | Status | Priority | Assigned To | Notes
1 | Vite + React 18 scaffold; install React Router v6, Axios, CSS Modules | To Do | High
2 | Axios instance: base URL, JWT Authorization header interceptor, 401 redirect interceptor | To Do | High
3 | JWT stored in React context (never localStorage); clear on logout | To Do | High
4 | Login page: email + password form, inline validation, error toast (UC-001, UC-009, UC-014) | To Do | Medium
5 | Signup page (Tester only): name, email, password, confirm password, role=Tester hardcoded (UC-013) | To Do | Medium
6 | ProtectedRoute component: checks auth context, redirect to /login if unauthenticated | To Do | Medium
7 | RoleRoute component: checks user role, shows 403 page if wrong role | To Do | Medium
8 | Logout flow: POST /api/auth/logout, clear context, redirect to /login (UC-020) | To Do | Low
9 | Reusable loading spinner and skeleton placeholder components | To Do | Low

## S9-Admin
Sprint 9 — Admin Dashboard
Phase 2 — Frontend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 10
# | Task Description | Status | Priority | Assigned To | Notes
1 | Admin dashboard layout: sidebar nav (Bugs, Manage Users, Logout) + topbar with avatar | To Do | High
2 | Bug list table: ID, title, severity badge, status badge, assignee, date, actions (edit/delete) | To Do | High
3 | Table client-side sort by any column and filter by status / severity pill chips | To Do | High
4 | Add Bug modal form: title, description, severity, developer dropdown — POST /api/bugs (UC-003) | To Do | Medium
5 | Edit Bug modal: pre-filled from selected row — PUT /api/bugs/{id} (UC-004) | To Do | Medium
6 | Delete Bug: confirmation dialog with bug title — DELETE /api/bugs/{id} (UC-005) | To Do | Medium
7 | Manage Users page: table of all users with Edit and Delete per row (UC-006) | To Do | Medium
8 | Update User Profile modal: email + phone only — PUT /api/users/{id} (UC-007) | To Do | Low
9 | Delete User: confirmation dialog — DELETE /api/users/{id} (UC-008) | To Do | Low
10 | Toast notification system (success / error) on every API action | To Do | Low

## S10-DevDash
Sprint 10 — Developer Dashboard
Phase 2 — Frontend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 9
# | Task Description | Status | Priority | Assigned To | Notes
1 | Developer dashboard layout: sidebar (My Bugs, Logout) + topbar (UC-010) | To Do | High
2 | Assigned bugs table: title, severity, status, test result, filed date, actions | To Do | High
3 | Update Status: inline dropdown per row (Open/In Progress/Resolved/Closed) — PATCH (UC-011) | To Do | High
4 | Confirmation popover before status change: current → new status preview | To Do | Medium
5 | Email dispatch confirmation toast after status update | To Do | Medium
6 | Bug detail page (click row): full bug info + AI Generated Test section (UC-012) | To Do | Medium
7 | AI test script viewer: syntax-highlighted code block (highlight.js / Prism), Copy button | To Do | Medium
8 | Test result section: PASS/FAIL badge, executedAt timestamp, scrollable log output | To Do | Low
9 | Poll GET /api/bugs/{id}/test-result every 3s while PENDING; stop on PASS or FAIL | To Do | Low

## S11-Tester
Sprint 11 — Tester Dashboard
Phase 2 — Frontend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 9
# | Task Description | Status | Priority | Assigned To | Notes
1 | Tester dashboard: sidebar + stat cards (total filed, open count, AI tests, pass rate) | To Do | High
2 | My bugs table: title, severity, status, test result, date, View + Cancel actions | To Do | High
3 | Filter pills: All / Open / In Progress / Resolved — client-side filter (UC-015) | To Do | High
4 | Submit Bug modal: title, plain-English description, severity, assign to dev — POST (UC-016) | To Do | Medium
5 | AI generation feedback: spinner after submission, auto-refresh test result | To Do | Medium
6 | Cancel Bug: confirmation dialog, PATCH /cancel, disable Cancel for Resolved/Withdrawn (UC-018) | To Do | Medium
7 | Bug detail page: AI test script viewer + test result logs, read-only (UC-017) | To Do | Medium
8 | Change Password modal: current, new, confirm — PATCH /api/users/password (UC-019) | To Do | Low
9 | Inline validation on all forms: required, min-length, email format, password match | To Do | Low

## S12-Polish
Sprint 12 — Polish & QA
Phase 2 — Frontend ¦ AI-Powered Bug Tracker (AIBT-2026) ¦ Check off tasks as you complete them
Tasks |  | Completed |  | Progress
Total Tasks: 10
# | Task Description | Status | Priority | Assigned To | Notes
1 | Responsive layout audit: all dashboards work at 1280px and 1024px minimum | To Do | High
2 | Dark mode: CSS variables / media query implementation across all pages | To Do | High
3 | Empty state illustrations for tables with zero results | To Do | High
4 | Error boundary components: catch render errors, show friendly fallback UI | To Do | Medium
5 | Accessibility pass: ARIA labels on all interactive elements, keyboard navigation for modals | To Do | Medium
6 | Cross-browser test: Chrome, Firefox, Edge — verify JWT flow end-to-end | To Do | Medium
7 | E2E smoke test: Tester signup → submit bug → AI test → Developer status update → Tester sees result | To Do | Medium
8 | .env.production config (API base URL, AI key placeholder), README with setup steps | To Do | Low
9 | Dockerfile for frontend (nginx) + docker-compose linking backend + frontend + PostgreSQL | To Do | Low
10 | Final team review, bug bash, sign-off against all 20 use cases (UC-001 to UC-020) | To Do | Low